## Jadwal Project
Hari | Fase | Halaman / Task | Detail Pengerjaan | Tabel/Field Terkait (ERD) | Status
1 | Fase 1 - UI Public | Fix Hero + Promo section | Beresin header sticky (top-0 + cek overflow parent), Promo (button + responsive di mobile), cek konsistensi Hero | - | Belum Mulai
2 | Fase 1 - UI Public | Halaman Home - Listing Produk | Grid produk (image_url, name, price), filter by category_id, badge diskon jika ada, dummy data dulu | products, categories | Belum Mulai
3 | Fase 1 - UI Public | Halaman Kategori | List semua categories, klik kategori -> filter produk by category_id | categories, products.category_id | Belum Mulai
4 | Fase 1 - UI Public | Halaman Detail Produk | Route /produk/[id] atau [sku], tampilkan name, price, description, image_url, qty stok (disable Add to Cart jika qty=0) | products (sku, price, qty, description, image_url) | Belum Mulai
5 | Fase 1 - UI Public | Halaman Cart (UI dulu, state lokal) | List cart_items (product_id, qty, price), update qty, hapus item, subtotal & total. Field price di-snapshot saat add (bukan selalu ambil dari products.price terbaru) | cart, cart_items | Belum Mulai
6 | Fase 1 - UI Public | Halaman Login & Register | Form register (username, email, password, no_hp), form login. Belum connect API, validasi form dulu | users (email, password NN, no_hp) | Belum Mulai
7 | Fase 1 - UI Public | Halaman Checkout | Form shipping_address, ringkasan order dari cart_items, tampilkan total_amount. Submit masih dummy/local | orders (shipping_address, total_amount) | Belum Mulai
8 | Fase 1 - UI Public | Halaman Riwayat Order (customer) | List orders milik user login (invoice, status, total_amount, created_at), klik -> detail order_details | orders, order_details | Belum Mulai
9 | Fase 1 - UI Public | Search + Review Fase 1 | SearchBar filter produk by name (dummy dulu), cek semua halaman responsive mobile/desktop, commit git per fitur | products.name | Belum Mulai
10 | Fase 2 - DRF Backend | Setup project + model: roles, users | Init Django+DRF, model Role (name), model User custom (role_id FK, username, email, password, no_hp) - pertimbangkan extend AbstractUser | roles, users | Belum Mulai
11 | Fase 2 - DRF Backend | Model: categories, products | Model Category (name, description), model Product (category_id FK, sku, name, qty, price, image_url, description, soft-delete pakai deleted_at) | categories, products | Belum Mulai
12 | Fase 2 - DRF Backend | Model: cart, cart_items | Model Cart (user_id FK, 1:1 atau 1:banyak sesuai kebutuhan), model CartItem (cart_id FK, product_id FK, qty, price snapshot) | cart, cart_items | Belum Mulai
13 | Fase 2 - DRF Backend | Model: orders, order_details | Model Order (user_id FK, invoice auto-generate, status, total_amount, shipping_address), model OrderDetail (product_id FK, order_id FK, qty, price_per_unit, subtotal) | orders, order_details | Belum Mulai
14 | Fase 2 - DRF Backend | Serializer + endpoint Categories & Products | GET/POST/PUT/DELETE /api/categories/, GET /api/products/ (filter by category, search by name), GET /api/products/<id>/, exclude soft-deleted (deleted_at IS NULL) | categories, products | Belum Mulai
15 | Fase 2 - DRF Backend | Endpoint Auth (JWT) + Role | Install simplejwt, POST /api/register/, POST /api/login/, endpoint cek role_id (customer vs admin) untuk permission | users, roles | Belum Mulai
16 | Fase 2 - DRF Backend | Endpoint Cart | GET /api/cart/ (cart milik user login), POST /api/cart/items/ (tambah item), PATCH/DELETE /api/cart/items/<id>/ | cart, cart_items | Belum Mulai
17 | Fase 2 - DRF Backend | Endpoint Order (checkout) | POST /api/orders/ (dari cart_items -> generate order + order_details, validasi qty stok produk, kurangi products.qty, generate invoice unik) | orders, order_details, products.qty | Belum Mulai
18 | Fase 2 - DRF Backend | CORS + connect Next.js ke DRF | django-cors-headers, ganti semua dummy data Hari 2-9 jadi fetch API asli, test end-to-end (browse - cart - checkout) | - | Belum Mulai
19 | Fase 3 - Dashboard Admin | Setup project + Login Admin | Init React/Vue (Vite), halaman login khusus role_id admin, protected route, redirect jika role bukan admin | users.role_id, roles | Belum Mulai
20 | Fase 3 - Dashboard Admin | Halaman Manajemen Kategori | List categories (tabel), tambah/edit/hapus kategori | categories | Belum Mulai
21 | Fase 3 - Dashboard Admin | Halaman Manajemen Produk | List products (tabel: sku, name, qty, price), form tambah/edit (termasuk upload image_url), soft-delete (set deleted_at, bukan hapus row) | products | Belum Mulai
22 | Fase 3 - Dashboard Admin | Halaman Manajemen Order | List orders (invoice, user, status, total_amount), detail order -> tampilkan order_details, update status order | orders, order_details | Belum Mulai
23 | Fase 3 - Dashboard Admin | Halaman Manajemen User & Role (opsional) | List users beserta role, ubah role_id user (misal promote jadi admin) | users, roles | Belum Mulai
24 | Fase 3 - Dashboard Admin | Polish + testing integrasi 3 layer | Cek alur: admin ubah stok produk -> reflect ke public store, admin update status order -> reflect ke riwayat order customer | - | Belum Mulai
25 | Fase 4 - Security | Testing XSS + CSRF | Inject <script> di form (name produk, description, no_hp, shipping_address), cek CSRF protection di endpoint POST/PATCH | products, orders, users | Belum Mulai
26 | Fase 4 - Security | Testing Auth, IDOR, Role Bypass | Akses endpoint admin tanpa token, akses order user lain via ganti ID URL, coba akses dashboard admin dengan role customer | orders, users.role_id | Belum Mulai
27 | Fase 4 - Security | Fix temuan + dokumentasi | Perbaiki vulnerability yang ditemukan, tulis catatan (buat portofolio/interview): apa yang ditemukan & cara fix | - | Belum Mulai
28 | Fase 5 - Dockerize | Dockerize tiap service | Dockerfile Next.js, Django, dashboard (static build via Nginx) | - | Belum Mulai
29 | Fase 5 - Dockerize | Docker Compose | docker-compose.yml semua service + PostgreSQL, fix env vars & networking antar container | - | Belum Mulai
30 | Fase 5 - Dockerize | Testing full local via Docker | docker compose up, pastikan semua service komunikasi (termasuk DB), fix bug env/path | - | Belum Mulai
31 | Fase 6 - Deploy | Setup VPS + domain | Beli domain, arahkan DNS (A record ke 3 subdomain), setup Nginx reverse proxy | - | Belum Mulai
32 | Fase 6 - Deploy | Deploy semua service | docker compose up -d di VPS, setup SSL Certbot, testing end-to-end di domain asli | - | Belum Mulai

## Ringkasan Fase
Fase | Jumlah Hari | Fokus Belajar
Fase 1 - UI Public | 9 | Next.js, komponen UI per halaman (home, kategori, produk, cart, auth, checkout, riwayat order)
Fase 2 - DRF Backend | 9 | Django REST Framework, model sesuai ERD, serializer, JWT auth, CORS
Fase 3 - Dashboard Admin | 6 | React/Vue, integrasi multi-frontend ke 1 backend, role-based access
Fase 4 - Security | 3 | XSS, CSRF, IDOR, role bypass testing di project sendiri
Fase 5 - Dockerize | 3 | Docker, Docker Compose, container networking
Fase 6 - Deploy | 2 | VPS, domain, Nginx reverse proxy, SSL

## Referensi ERD
Tabel | Field Penting | Catatan
roles | id, name | Master role (misal: customer, admin)
users | role_id (FK), username, email (NN), password (NN), no_hp | role_id nentuin akses customer vs admin
categories | id, name (NN), description | Master kategori produk
products | category_id (FK), sku (NN), name (NN), qty (NN), price (NN), image_url (NN), deleted_at | deleted_at = soft delete, jangan hard delete produk
cart | id, user_id (FK) | 1 user idealnya 1 cart aktif
cart_items | cart_id (FK), product_id (FK), qty (NN), price (NN) | price di sini snapshot harga saat add to cart
orders | user_id (FK), invoice (NN), status (NN), total_amount (NN), shipping_address | invoice harus unik, generate otomatis saat checkout
order_details | product_id (FK), order_id (FK), qty (NN), price_per_unit (NN), subtotal | snapshot harga saat order, jangan reference ke products.price langsung